## Sheet1
Review-ID | Section ID | Date | Document Source | Version | Owner | Reviewer | Status | What to Change | Status by Owner | Date of Modifaction
1 | 1.2 | 17/04/2018 | Software requirements Specifications (SRS) | 2 | yassamin alaa | Mina | Done | Determination the type of matrial the device can be measure
2 | 2.1.2 (2) | [6 empty] | should be know time the result appear in the screen when the measure
3 | 2.2.1 | [6 empty] | more details like name the data sheet
4 | 2.2.2 | [6 empty] | more details like name the data sheet
5 | 2.2.3 | [6 empty] | more details like name the data sheet
6 | 2.2.4 | [6 empty] | more details like name the data sheet
7 | 2.2.6 | [6 empty] | determination the scale time ,scale speed
8 | 2.2.7 | [6 empty] | determination the scale time ,scale speed
9 | 2.2.8 | [6 empty] | please refer the number of function caver this point
10 | 2.2.9 | [6 empty] | should be make sure the screen was clear and appear only ome function
11 | 2.2.10 | [6 empty] | what the error message should be appear (check the customer need )
12 | 2.2.11 | [6 empty] | change appear in the screen or appear the final result
13 | 2.2.13 | [6 empty] | more details what mean barriers
14 | 2.3.1 | [6 empty] | what the error massage should appear
15 | 2.5 | [6 empty] | ( should be confirmed with customer )
15 |  | 18/04/2018 | Review Log | 2 | Ahmed Osama | Mahmoud Ibrahim | Need Modification | The review log Needs some modifications : 1- New Column must be added for Section Number 2- Doc ID must be Drop down menu with Certain IDs according to doc structure 3- Dates format must be fixed 4- Source column must be Drop down menu according to doc structure 5- All names must be Drop down menu with Certain 6- All Status column must be Drop down menu with fixed status with colors. 7- Header row would be better if it's floating with you downwards | Done | 18/04/2018
16 |  | 18/04/2018 | Git Hub Project Structure |  | Ahmed Osama | Mahmoud Ibrahim | Need Modification | The Project repository needs to be organized (documents must have unified format DocName_ID without any Version number (this one will be a tag on the tool) ) | Done | 18/04/2018
18 |  | 17/04/2018 | Project Plan | 1 | Omnia | Ahmed Osama | Done | 1- Too much details in the header
19 | [7 empty] | 2- Revision Table is missing
20 | 1.1 | [6 empty] | 3-change "All team members "
21 | 1.2 | [6 empty] | 4-change " Two"
22 | 1.2 | [6 empty] | 5-write what "WBS" refers to ? And RASIC as well
23 | 1.3 | [6 empty] | 6-write "who approves Changes"
24 | 2 | [6 empty] | 7- need more details in Project Scope Section
25 | 2.1.1 | [6 empty] | 8-write Client objectives not Company objectives
26 | [7 empty] | 9-the format of whole document is missing
27 | 4.1 | [6 empty] | 10-no need for Advantages of V model
28 | 4.1 | [6 empty] | 11-no need for Disadvantages of V model
30 | 4.3 | [6 empty] | 12- Github is Cloud Storage Server . Git Extensions instead
31 | 4.4.1 | [6 empty] | 13- write each task for every person on the team and more details
32 | 5 | [6 empty] | 14-more information in Communication Plan
33 | 6.1 | [6 empty] | 15- Insert WBS table
34 | 6.2 | [6 empty] | 16-insert Git as CM tool