## Sheet1
Review-ID | Section ID | Date | Document Source | Version | Owner | Reviewer | Status | What to Change | Status by Owner | Date of Modifaction
1 | 1.2 | 17/04/2018 | Software requirements Specifications (SRS) | 2 | yassamin alaa | Mina | Need Modification | Determination the type of matrial the device can be measure
2 | 2.1.2 (2) | [6 empty] | should be know time the result appear in the screen when the measure
3 | 2.2.1 | [6 empty] | more details like name the data sheet
4 | 2.2.2 | [6 empty] | more details like name the data sheet
5 | 2.2.3 | [6 empty] | more details like name the data sheet
6 | 2.2.4 | [6 empty] | more details like name the data sheet
7 | 2.2.6 | [6 empty] | determination the scale time ,scale speed
8 | 2.2.7 | [6 empty] | determination the scale time ,scale speed
9 | 2.2.8 | [6 empty] | please refer the number of function caver this point
10 | 2.2.9 | [6 empty] | should be make sure the screen was clear and appear only ome function
11 | 2.2.10 | [6 empty] | what the error message should be appear (check the customer need )
12 | 2.2.11 | [6 empty] | change appear in the screen or appear the final result
13 | 2.2.13 | [6 empty] | more details what mean barriers
14 | 2.3.1 | [6 empty] | what the error massage should appear
15 | 2.5 | [6 empty] | ( should be confirmed with customer )
15 |  | 18/04/2018 | Review Log | 2 | Ahmed Osama | Mahmoud Ibrahim | Need Modification | The review log Needs some modifications : 1- New Column must be added for Section Number 2- Doc ID must be Drop down menu with Certain IDs according to doc structure 3- Dates format must be fixed 4- Source column must be Drop down menu according to doc structure 5- All names must be Drop down menu with Certain 6- All Status column must be Drop down menu with fixed status with colors. 7- Header row would be better if it's floating with you downwards | Done | 18/04/2018
16 |  | 18/04/2018 | Git Hub Project Structure |  | Ahmed Osama | Mahmoud Ibrahim | Need Modification | The Project repository needs to be organized (documents must have unified format DocName_ID without any Version number (this one will be a tag on the tool) ) | Done | 18/04/2018
18 |  | 17/04/2018 | Project Plan | 1 | Omnia | Ahmed Osama | Need Modification | 1- Too much details in the header | Done | 19/04/2018
19 | [7 empty] | 2- Revision Table is missing
20 | 1.1 | [6 empty] | 3-change "All team members "
21 | 1.2 | [6 empty] | 4-change " Two"
22 | 1.2 | [6 empty] | 5-write what "WBS" refers to ? And RASIC as well
23 | 1.3 | [6 empty] | 6-write "who approves Changes"
24 | 2 | [6 empty] | 7- need more details in Project Scope Section
25 | 2.1.1 | [6 empty] | 8-write Client objectives not Company objectives
26 | [7 empty] | 9-the format of whole document is missing
27 | 4.1 | [6 empty] | 10-no need for Advantages of V model
28 | 4.1 | [6 empty] | 11-no need for Disadvantages of V model
30 | 4.3 | [6 empty] | 12- Github is Cloud Storage Server . Git Extensions instead
31 | 4.4.1 | [6 empty] | 13- write each task for every person on the team and more details
32 | 5 | [6 empty] | 14-more information in Communication Plan
33 | 6.1 | [6 empty] | 15- Insert WBS table
34 | 6.2 | [6 empty] | 16-insert Git as CM tool
35 | TC1.0 | 18/04/2018 | Test_Cases |  | Mona Ahmed | Mahmoud Ibrahim | Needs Modification | What do you mean with Valid scenario it's better to mention the scenario in the definition to be clear from the beginning | Done | 19/4/2018
36 | TC1.0 | [6 empty] | Preconditions can be simplified as the prototype must be built up and ready for testing -There are no steps need to be mentioned | Done | 19/4/2018
37 | TC1.0 | [6 empty] | In the steps ,in addition to giving the upper limit ,you have to mention a value to be taken as example and to be measured in the excution(Expected result) | Negotiate | 19/4/2018 | if I take aspecific value I will ignore a lot of ather values , it is accpeted range not specific value
38 | TC1.1 | [6 empty] | Title needs to be clear and straight forward | Done | 19/4/2018
39 | TC1.1 | [6 empty] | Preconditions can be simplified as the prototype must be built up and ready for testing -There are no steps need to be mentioned | Done | 19/4/2018
40 | TC1.1 | [6 empty] | In the steps ,in addition to giving the upper limit ,you have to mention a value to be taken as example and to be measured in the excution(Expected result) | Negotiate | 19/4/2018 | if I take aspecific value I will ignore a lot of ather values , it is accpeted range not specific value
41 | TC1.2 | [6 empty] | Preconditions can be simplified as the prototype must be built up and ready for testing -There are no steps need to be mentioned | Done | 19/4/2018
42 | TC1.2 | [6 empty] | In the steps ,in addition to giving the upper limit ,you have to mention a value to be taken as example and to be measured in the excution(Expected result) | Negotiate | 19/4/2018 | if I take aspecific value I will ignore a lot of ather values , it is accpeted range not specific value
43 | TC1.3 | [6 empty] | Preconditions can be simplified as the prototype must be built up and ready for testing -There are no steps need to be mentioned | Done | 19/4/2018
44 | TC1.3 | [6 empty] | In the steps ,in addition to giving the upper limit ,you have to mention a value to be taken for the angle and the distance as example and to be measured in the excution(Expected result) | Negotiate | 19/4/2018 | if I take aspecific value I will ignore a lot of ather values , it is accpeted range not specific value
45 | TC1.4 | [6 empty] | Is "Undefine Object " is the final error message,if its its not clear enough for user, we have to find a better one | Closed | 19/4/2018 | Message is approved by Customer, and the development team approved it.
46 | TC1.4 | [6 empty] | Preconditions can be simplified as the prototype must be built up and ready for testing -There are no steps need to be mentioned | Done | 19/4/2018
47 | TC1.4 | [6 empty] | In the steps ,in addition to giving the upper limit ,you have to mention a value to be taken for the angle and the distance as example and to be measured in the excution(Expected result) | Negotiate | 19/4/2018 | if I take aspecific value I will ignore a lot of ather values , it is accpeted range not specific value
48 | TC1.5 | [6 empty] | Is "Undefine Object " is the final error message,if its its not clear enough for user, we have to find a better one | Closed | 19/4/2018 | Message is approved by Customer, and the development team approved it.
49 | TC1.5 | [6 empty] | Preconditions can be simplified as the prototype must be built up and ready for testing -There are no steps need to be mentioned | Done | 19/4/2018
50 | TC1.5 | [6 empty] | In the steps ,in addition to giving the upper limit ,you have to mention a value to be taken for the angle and the distance as example and to be measured in the excution(Expected result) | Negotiate | 19/4/2018 | if I take aspecific value I will ignore a lot of ather values , it is accpeted range not specific value
51 | TC1.6 | [6 empty] | Preconditions can be simplified as the prototype must be built up and ready for testing -There are no steps need to be mentioned | Done | 19/4/2018
52 | TC1.7 | [6 empty] | Preconditions can be simplified as the prototype must be built up and ready for testing -There are no steps need to be mentioned | Done | 19/4/2018
53 | TC1.7 | [6 empty] | In the steps ,in addition to giving the upper limit ,you have to mention a value to be taken for the angle and the distance as example and to be measured in the excution(Expected result) | Negotiate | 19/4/2018 | if I take aspecific value I will ignore a lot of ather values , it is accpeted range not specific value
54 | TC1.8 | [6 empty] | Is "Undefine Object " is the final error message,if its its not clear enough for user, we have to find a better one | Closed | 19/4/2018 | Message is approved by Customer, and the development team approved it.
55 | TC1.8 | [6 empty] | Preconditions can be simplified as the prototype must be built up and ready for testing -There are no steps need to be mentioned | Done | 19/4/2018
56 | TC1.8 | [6 empty] | In the steps ,in addition to giving the upper limit ,you have to mention a value to be taken for the angle and the distance as example and to be measured in the excution(Expected result) | Negotiate | 19/4/2018 | if I take aspecific value I will ignore a lot of ather values , it is accpeted range not specific value
57 | TC1.9-TC1.13 | [6 empty] | Same comment as TC1.8 | Done | 19/4/2018
58 | TC2.0 -TC2.13 | [6 empty] | Same comment as TC1.0-TC1.13 | Done | 19/4/2018
59 | TC3.0 -TC3.12 | [6 empty] | Same comment as TC1.0-TC1.13 | Done | 19/4/2018
60 | REQ 2.2.6 | 19/4/2018 | SRS | 2_0 | Yasmin Alaa | Mona Ahmed | Need Modification | this isn't requirement to validate the system as it is validation to equation will be written in the code and this change approved by asking eng/Ramadan
61 | REQ 2.2.7 | 19/4/2018 |  |  | Yasmin Alaa | Mona Ahmed | Need Modification | this isn't requirement to validate the system as it is validation to equation will be written in the code and this change approved by asking eng/Ramadan
62 |  | 20/4/2018 | Component_Design_Document_LCD | 1.0.0 | RAMADAN/FELO | FELOPATER | DONE
63 | 1.4 | 20/4/2018 | Test Plan | 1 | Mahmoud/ Mina | Mona Ahmed | Need Modification | you have to mention any refrence materials will be used like crs and datasheets to HW
64 | 2 | 20/4/2018 |  |  | Mahmoud/ Mina | Mona Ahmed | Need Modification | you have to separate design into component and high level design
65 | 2.1 | 20/4/2018 |  |  | Mahmoud/ Mina | Mona Ahmed | Need Modification | you didn’t mention the button
66 | 7.2 | 20/4/2018 |  |  | Mahmoud/ Mina | Mona Ahmed | Need Modification | in point 2 you didn't mentione WBS and other project plan sections
67 | 7.2 | 20/4/2018 |  |  | Mahmoud/ Mina | Mona Ahmed | Need Modification | in point 4 it is validation not verification
68 | 7.2 | 20/4/2018 |  |  | Mahmoud/ Mina | Mona Ahmed | Need Modification | in point 7 Assign bug report to whom ? you have to refer
69 | 7.4 | 20/4/2018 |  |  | Mahmoud/ Mina | Mona Ahmed | Need Modification | you didn’t refer all documents and resources to testing , we use tools like: excel
70 | 8.1 | 20/4/2018 |  |  | Mahmoud/ Mina | Mona Ahmed | Need Modification | · you didn’t mention power supply and switch
71 | 9 | 20/4/2018 |  |  | Mahmoud/ Mina | Mona Ahmed | Need Modification | poor details in this section and not understandable
72 |  | 2018-04-20 | HLD | 1 | RAMADAN | Mostafa | Need Modification | You should put the HLD In a Word file with a a describation for it