## Sheet1
ID | Question | Answer | Status | Who Asked | Who Answered | Date Asked | Due Date | Answers 02-04-2018
SIQ_1 | Is system(product) going to be on fixed or moving body? | The system is fixed at executing(fixed location),But portable as a system, and coustmer said (For now ). | Answered | Ahmed El-Dakak | Ramdan(Customer) | 31-3-2018 | 31-3-2018
SIQ_2 | Is the required object to measure fixed or movable? | object is movable. | Answered | Mahmoud Ibrahim | Ramdan | 31-3-2018 | 31-3-2018
SIQ_3 | Is there any kind of required casing for product? | Not a specific casing, but product can be moved easily . | Need more details | Yasmin Alaa | Ramdan | 31-3-2018 | 31-3-2018 | It is up to you
SIQ_4 | what is the power required for product? | Normal Battery (not rechargeable). | Answered | Mahmoud Ibrahim | Ramdan | 31-3-2018 | 31-3-2018 | Disposable battery not rechargeable
SIQ_5 | Is there any specific types for hardware in the system? | It is up to technical team to define | Renegotiate | Ahmed El-Dakak | Ramdan | 31-3-2018 | 31-3-2018 | I cannot decide every type of used hardware as it is up yo technical team, I just want it to fit with project requirement with low costs to you.
SIQ_6 | In the CRS there are two types of screens wanted LCD & LED , we need more details about these types ? | Just a LCD screen, LED was a mistake. | Answered | Ahmed El-Dakak | Ramdan | 31-3-2018 | 31-3-2018
SIQ_7 | What is the LCD required size? | Not defined yet,But we offerd the known size (16*2)LCD | Not Answered | Yasmin Alaa | Ramdan | 31-3-2018 | 31-3-2018 | you have to define it with my requirements, you can use the one that can be used to display the formate that i have mensioned before
SIQ_8 | What is the required type of Ultrasonic sensor? | It is up to technical team to define | Answered | Ahmed Ramdan | Ramdan | 31-3-2018 | 31-3-2018
SIQ_9 | What is the maximum distance for Ultrasonic to measure? | According to the maximum distance for Ultrasonic to measure | Renegotiate | Yasmin Alaa | Ramdan | 31-3-2018 | 31-3-2018 | it is up to the kind of the sensor, technical team can define it based on the one that fits with requirements
SIQ_10 | What is the accuracy wanted ? | According to Ultrasonic accuracy. | Renegotiate | Mahmoud Ibrahim | Ramdan | 31-3-2018 | 31-3-2018 | It depends on the used HW, up to technical team
SIQ_11 | Is there a specific size of object to detect? | According to Ultrasonic angle range 15 degree,,which is acceptable with customer. | Answered | Yasmin Alaa | Ramdan | 31-3-2018 | 31-3-2018
SIQ_12 | What is the response time required for measureing velocity? | Real-Time (measure occurs at any change for the object). | Answered | Mahmoud Ibrahim | Ramdan | 31-3-2018 | 31-3-2018
SIQ_13 | Is there required sampleing rate to measure distance or detect object velocity? | What you need to be Real-Time,but we can get more information about Ultrasonic specs and renegotiate. | Renegotiate | Ahmed Ramdan | Ramdan | 31-3-2018 | 31-3-2018 | Kindly clarify the question
SIQ_14 | More sampling rate ,More power consumption ,Is that okay ? | customer said: yes, it's my requirments. | Renegotiate | Ahmed El-Dakak | Ramdan | 31-3-2018 | 31-3-2018 | Kindly clarify the question
SIQ_15 | Ultrasonic sensor will determine the maximum and minimum limitation for the system? | customer said: okay, but get back to me with these limitation. | Renegotiate | Ahmed El-Dakak | Ramdan | 31-3-2018 | 31-3-2018 | Kindly clarify the question; if you mean the distance limit for the sensor, it is up to you as you have to choose the suitable sensor, and by default the limitation will be defined by the sensor your will choosen itself
SIQ_16 | Is the system always in active mode or controlable with switches? | Always in active mode, but we discuss the impact of that requirment on battery lifetime ,and finally customer wanted two buttons (start & stop). | controlable | Mahmoud Ibrahim | Ramdan | 31-3-2018 | 31-3-2018 | Not 2 buttons, just one On/Off button refer to SIQ_24
SIQ_17 | Is there any reset button for the system? | No need for reset button. | Answered | Ahmed El-Dakak | Ramdan | 31-3-2018 | 31-3-2018 | just On/Off button
SIQ_18 | What is the display format on LCD ? | Distance: (digit)mm , Velocity: (digit)m/s | Answered | Ahmed Ramdan | Ramdan | 31-3-2018 | 31-3-2018 | Example for illustation: Distance: 20.0 mm Velocity: 10.0 m/s
SIQ_19 | What is the unit fraction to display? | No specific unit yet , but we informed the customer that it's limited with LCD size . | Not Answered | Ahmed El-Dakak | Ramdan | 31-3-2018 | 31-3-2018 | Distance Milli Meter will be displayed on screen mm Velocity Meter/Second will be displayed on screem m/s
SIQ_20 | What is the default state of the LCD? | Distance: 0mm , Velocity: 0m/s | Renegotiate | Mahmoud Ibrahim | Ramdan | 31-3-2018 | 31-3-2018 | Kindly clarify you question; if you mean while the system begin?
SIQ_21 | What is the required message to display when no object detected ? | Undefined object , but it's to long for LCD to display ,so customer will get back with updates. | Not Answered | Ahmed Ramdan | Ramdan | 31-3-2018 | 31-3-2018 | The LCD displays the word "undefined distance" and "undefined speed" if the screen won't able to display the whole word you can make it rotatable in case you can do it; if this is an extra technical work get back to me again
SIQ_22 | what is the acception criteria to you ? |  | Answered | Mona Ahmed | Ramdan | 2018-02-04 |  | Working system as per requirements
SIQ_23 | Do you want the delivery to be in white board or PCB ? |  | Answered | Mona Ahmed | Ramdan | 2018-02-04 |  | I do not mind to use any one of them, you can use which the lower in cost, but take into consideration that you have to deliver this project to a customer as well
SIQ_24 | What is the type of (ON/OFF) switch wanted ? |  | Answered | Ahmed El-Dakak | Ramdan | 2018-02-04 |  | traditional On/Off switch
SIQ_25 | Do you want to measue the distance and velocity for object moving vertical or Horizontal? |  | Answered | Mona Ahmed | Ramadan | 2018-03-04 |  | It depends on used sensor; if it can measure distance and velocity for movable object in only horizontal direction or vertical direction only , it's OK, I do not mind. if it can measure V & D for both directions it's good. It's up to used sensor
SIQ_26 | can you explain to us the maximum error rate to the product? |  | Answered | Mona Ahmed | Ramadan | 2018-04-04 |  | I have answered to this question before, and I said that It depends on used sensor; refer to technical team
SIQ_27 | the message when object isn't in the measurable area or not put ? |  | Answered | Mona Ahmed | Ramadan | 14/4/2018 |  | "Undefined Object"
SIQ_28 | Asking about Requirements 2.2.6 and 2.2.7 in SRS that we can write test cases to validate system using them ? | it is validation to the equations used in code to measure distance and velocity , and it is not the major in validating system as it is in the code. | Answered | Mona Ahmed | Ramadan | 18/4/2018